Practical – 5

AIM:

Software Project Estimations & Planning for the Automatic Dataset Annotation System.

1. Project Overview

The core objective of this project is to automate the tedious process of manual image labeling for Computer Vision. The system utilizes the Segment Anything Model (SAM) and text-based detection to identify objects and automatically generate high-quality segmentation masks and bounding boxes.

2. Function Point (FP) Calculation

Function Point analysis measures the size of the software based on the functionality it provides to the user.

Identification of Components

| Component Type | Description | Count |
| --- | --- | --- |
| External Input (EI) | Dataset Upload, Object Class Prompt, Setting Thresholds | 3 |
| External Output (EO) | Visual Mask Overlays, Exported Annotation Files (YOLO/COCO) | 2 |
| External Inquiry (EQ) | Previewing specific image labels, Fetching processing status | 2 |
| Internal Logical File (ILF) | Image Path Database, Label Configuration File | 2 |
| External Interface File (EIF) | Pretrained SAM Model, Grounding AI Model Bindings | 2 |

Calculate Unadjusted FP (UFP)

| Type | Count | Weight | Total |
| --- | --- | --- | --- |
| EI | 3 | 4 | 12 |
| EO | 2 | 5 | 10 |
| EQ | 2 | 4 | 8 |
| ILF | 2 | 10 | 20 |
| EIF | 2 | 7 | 14 |
| Total |  |  | 64 |

Value Adjustment Factor (VAF)

Assuming a standard Degree of Influence across 14 characteristics (Total GSC = 28).

- VAF = 0.65 + (0.01 * 28) = 0.93

Final Function Points

- FP = UFP * VAF

- FP = 64  * s 0.93 = \mathbf{59.52}  (Approx. 60 FP)

3. COCOMO Model Estimation

The COCOMO model estimates effort and time based on the project's size in KLOC.

Project Parameters:

- Mode: Organic (Small team, familiar environment).

- Estimated Size: 5 KLOC (Estimated for Python orchestration and annotation logic).

- Constants:  a = 2.4, b = 1.05, c = 2.5, d = 0.38

A.

Effort Calculation (Person-Months)

- E = a  * s (KLOC)^b

- E = 2.4  * s (5)^{1.05} 2.4  * s 5.4

- Effort = 12.96 Person-Months

B.

Development Time (Months)

- T = c  * s (E)^d

- T = 2.5  * s (12.96)^{0.38} = 2.5  * s 2.65

- Time = 6.6 Months

C.

Team Size

- Team Size =  Effort /  Time

- Team Size = 12.96 / 6.6 2  Developers

2) Develop a Software Project Management Plan using Microsoft Project / JIRA / Redmine Tool

Gantt Chart